## Sheet1
Iteration #1 | Feature | Feature | Feature | Feature
Date of milestone Nov 10th 2019
Features in scope | Answer Question | Calculate Loan
Features implemented | Answer Question | Calculate Loan
Features in deficit this Iteration
Iteration Comments & Summary | Encountered issue with QnA Maker cost
Iteration #2
Date of milestone November 24th 2019
Features in scope | Proceed with loan | database storage
Features implemented | Proceed with loan
Features in deficit this Iteration |  | database storage
Iteration Comments & Summary |  | to be implemented this week
Iteration #3
Date of milestone February 16th 2020
Features in scope | deploy to azure
Features implemented | deploy to azure
Features in deficit this Iteration | cosmos db
Iteration Comments & Summary | function calc update + tests
Iteration #4
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary